## Website
S. No. | Changes | Screenshots | Update | Any Remarks
1 | Destination mapping is not required since all the travel agents are multiple destinations |  | Done | Done, Now you can give specific destination or all destination to any operation person,
2 | If TAT is not followed, what is the effect? |  | Done | Email will be sent to operations persons
3 | D-7 (By default supplier payment)- Where?
4 | Alert mails should be sent to all the agents one day prior for making due payments to the hotels
5 | Editable amount |  | Done
6 | Please add Payment Receipt Button, Amount, Attachment and Description, after payment received from the client |  | Awaiting
7 | Create Group ID |  | Done
8 | Where to exracts reports from on CRM? |  | Awaiting
9 | New Query- Need ADD AGENT in dialog box |  | Awaiting
10 | Add Agent- Need an option for file download so we can attach an excel with all agents which is automatically uploaded in the CRM |  | Done
11 | Agent Company type should not be mandatory |  | Awaiting
12 | After selecting state this alert message keeps on popping up and it does not let me save the agent |  | Awaiting
13 | Add New Query- We have options B2B, B2C and Corporate |  | Awaiting
14 | How to add sales persons as operation persons as well since some of them carry both activities? |  | Done
15 | How to change assigned persons name after assigning the query |  | Done
16 | Partial Payment done but it is showing as full amount paid |  | Done
17 | Deboxglobal id should be removed |  | Awaiting
18 | We should be able to confirm query after generating invoice |  | Done
19 | Voucher should be generated in PDF form not word |  | Awaiting
20 | Change configured email id to query@dishavoyage.com
21 | Need a tab to send invoice to the agent |  | Awaiting

## Sheet1
CRM Tracker
S. No. | Changes | Status | Any Remarks
1 | On query Cancellation, System should ask to cancell Vocuher and Invoice | Done
2 | Option to Select Multiple Destination | Pending
3 | Need to one more user category - Account Manager,Sales, Operations | Done
4 | In Query Option, Followup - Need Calender to set Follow-up Date like Outlook etc. | Pending | But need option to define time too
5 | In Query Communcation, need option to enter internal communication | Done
6 | Option to attach file from Document Management | Done
7 | Document Management , by default should show List View | Done
8 | In Contact Management - Contact Person should be come prior to Sales Person | Done
9 | CRM Dash Board | Pending
10 | Sales Module with Mobile App | Pending
11 | Supplier Communcation | Pending
12 | itinerary builder | Pending
13 | Website CRM Integration | Pending
14 | Voucher and Invoice should be generated in PDF | Pending
15 | Query Page which can be integrated on website to generate query from there with status of webquery | Pending
17 | Disha Requirement on DMC Payment | Pending
18 | Option to select Multiple Hotel Category Type | Pending
19 | Need to give two options of Add Company and Add Client in Query Management so user can directly create Company or B2C while creating any new query | Pending
20 | Need to give option to generate invoice directly from Query as we are able to generate only Voucher from here. | Pending
21 | In voucher, need to give one more option to search by company with From Date and To Date Filter as for corporate, One Click send all monthly invoice by end of every month. | Pending
22 | Remove Payment request from Menu bar and add two more options, Quotation and Itinerary | Pending
23 | In Login page, give option of Forgot Password, we will take user email id and password will be sent on user’s email id. | Pending
Regards
Dinesh Khari